## Sheet1
Weird Areas
Route_Name | Issue | Matches another Route? | Proposed Fix | Loc Name | Approved Fix | Notes | Fixed? | Tried to fix/notes
101-F-2 | Should use 20174, 25580, 25581, 25582 | 101-R-1 | Add points to shapes.txt |  | edit shapes |  | done | y
104-F-1 | Should use 97098, 102252, 51857 | 105-F-1, 109-F-1, 109-F-2 | Add points to shapes.txt | Sullivan Sq | edit shapes | fixed with shape vs stop pattern issue | done
104-R-1 | Should use 50780, 33019, 33024, 50788, 102827, 129369, 33020, 95912, 50787, 50788 | 105-R-1, 109-R-1 | Add points to shapes.txt | Sullivan Sq | edit shapes | lower priority |  | y
105-F-1 | Should use 11113 |  | Fix DIR |  | fix dir |  | x
106-F-2 | Should use Santilli Circle (10132, 10134, 10133, 10130) | 106-F2, 99-F-1, 110-F-1, 110-F-2, 112-R-1 | Fix DIR or add points to shapes.txt | Santilli Circle | add turn prohibition |  | x
106-R-1 | Missing stop 5859 |  | Unsure if we care - but it’s not a start or end stop. |  | remove stop | z | done | y
106-R-2 | Should not be using (10132, 10134, 10133, 10130, 45358, 97039, 17319, 17321, 17320) |  | Absolutely no idea - add points to shapes.txt? This is odd behavior |  | low priority investigate further |  | done
11-R-1 | Should use (97364, 97363, 75113, 32751, 75112, 86649, 32750, 74989, 75116, 75115) | 47-F-1, 47-R-1, 9-R-1 | DIR issues? |  | known issue |  | x
112-F-1 | This route is bananas in the middle |  | add points to shapes.txt |  | cosmetic |  | x
112-R-1 | This route is bananas in the middle | 114-R-1 | Add points to shapes.txt |  | cosmetic |  | x
132-F-1 | doubles back at start/end of route |  | move last stop closer to available link |  | move stop | z | done | y
136-R-1 | doubles back incorrectly, may not care | 137-R-1 | move stop point (6771/6670) |  | cosmetic |  | x
16-R-3 | route end should take longer path | 16-R-4, 8-F-1, 8-F-2, 8-R-1, 8-R-2 | Add points to shapes.txt | JFK | fix jfk loop shapes.txt |  |  | y
170-F-1 | MassPike splits off incorrectly | 505-F-1 | Add points to shapes.txt |  | edit shapes |  |  | y
170-R-1 | MassPike splits off incorrectly, but dif direction so dif | 505-R-1 | Add points to shapes.txt |  | edit shapes |  | done | y
171-F-1 | Logan Airport is a mess | 741-F-1 | Add points to shapes.txt |  | cosmetic - review turn penalties |  | x
195-R-1 | Should go between Public Gardens and Boston Common | 43-R-1, 55-R-2 | add points to shapes.txt |  | edit shapes | delete
211-F-1 | wrong links at the end | 211-R-1, 217-F-1, 245-F-1, 245-R-1, 214-F-2, 214-F-3, 212-R-1, 214216-F-1, 215-R-1, 216-F-1, 220-F-1, 220-F-2, 221-F-1, 222-F-1, 222-F-2, 222-F-3, 225-F-1, 225-F-2, 225-F-3, 225-F-4, 225-F-5, 230-F-1, 236-F-1, 238-F-1, 238-F-2 | move stop point | Quincy Center | cosmetic |  | x
217-R-1 | end missing |  | investigate further | Quincy Center |  | cosmetic | done
225-R-3 | end missing |  | investigate further | Quincy Center |  | cosmetic | done
236-F-1 | weird loop back at end |  | investigate further | Quincy Center |  | cosmetic | done
325-F-1 | broken connections on imported, so missing stops on conflated |  | investigate further |  |  |  | done
326-F-1 | missing a bunch of stops by taking a wrong turn | 326-R-1, 95-F-2, 95-R-1 | investigate further |  |  |  | done
34E-F-1 | odd middle bit | 34E-F-3, 34E-R-1, 34E-R-3, 35-F-2, 35-R-1, 52-F-1, 52-F-2, 52-R-1, 52-R-2 | update shapes.txt |  | move stops, delete legs |  | done | y
350-F-1 | missing end of route? 350-F-2 has it though? |  | investigate further |  |  |  | done
354-F-1 | on the wrong link for a while in middle | 354-R-1 | update shapes.txt |  | start at bottom
36-R-1 | beginning of route missing |  | investigate further |  |  | stop far from link | done
4-F-2 | should use 52751 and not go other direction |  | edit shapes.txt |  | edit shapes |  |  | y
4-R-1 | route begins on the wrong link/direction |  |  |  | edit shapes |  |  | y
40-F-1 | missing some links for stops at end of route | 40-R-1 | investigate further |  |  | move stops? | done | y
426-R-1 | takes wrong links in middle, unsure if worth fixing | 428-R-1 | edit shapes.txt |  | edit shapes
429-R-1 | odd interchange issues | 429-F-2, 429-F-3, 429-R-2 | edit shapes.txt |  | delete stop | z | done | y
436-R-1 | shouldn't go through the interchange | 436-R-2, 436-F-2, 436-F-1, | move stops & edit shapes.txt |  | delete 2 stops | delete 96110 or make not unidirectional | done | y
448-F-1 | stop on wrong side of link so makes odd choices (midpoint stop) & airport issues | 449-F-1 |  |  | very wrong fix | * 449-R and 448-R have airport issues too |  | wonderland
465-R-1 | odd route making odd choices |  | investigate further |  | cosmetic | not at all fixed | x
558-F-1 | missing big chunks of this route |  | investigate further |  |  |  | done
64-F-1 | missing end of the route |  | investigate further |  |  |  | done
67-R-1 | takes wrong link (33644) for short period | 62-R-1, 76-R-1, 84-R-1 | move stop |  | cosmetic |  | x
70-R-1 | missing last 3 stops |  | investigate further |  |  |  | done
708-R-1 | missing most of the route |  | investigate further |  |  | cosmetic update? | done
70A-F-1 | doesn't follow stops for last quarter of route |  | investigate further |  |  |  | done
71-F-1 | takes wrong link | 96-R-2, 72-R-1, 74-R-1, 75-R-1, 73-F-1, 71-R-1, 86-F-1, 78-R-1, 77-R-1, 73-R-1, 73-F-1, 746-F-1, 746-R-1, 75-F-1 | adjust shapes.txt to match R | Harvard SQ | change harvard stop location to be on bus tunnel |  |  | y
716-F-1 | should not go on hwy | 716-R-1 | extend link to prevent going on hwy (or move stops to not go beyond link) |  | delete 2 stop | z | done
743-F-1 | really messed up route except for tunnel | 742-F-1, 741-F-1 | adjust shapes.txt |  | SL - make new brt network |  | x
743-R-1 | beginning messed up but rest great | 742-R-1, 741-R-1 | adjust shapes.txt |  | SL - make new brt network |  | x
747-R-1 | shortcuts |  | probably not big enough to require updates to shapes.txt |  | tweak for union square |  |  | y
751-F-1 | South Station start/end |  | needs shapes.txt adjustment | South Station | edit shapes
76-R-1 | missing end/beginning of route |  | investigate further |  |  | cosmetic update? | done
84-F-1 | route beginning oddly | 351-F-1, 62-F-1, 62-F-2, 67-F-1, 76-F-1 | adjust shapes.txt |  | cosmetic |  | x
86-F-1 | 2 loopy things missing - hwy? |  | adjust shapes.txt | Harvard SQ | harvard tunnel
88-R-1 | smaller loop at one end | 94-R-1, 96-R-1, 89-F-1 | adjust shapes.txt |  | cosmetic |  | x
99-F-1 | misses odd loop, hwy? | 132-R-1 | not a big deal - adjust shapes.txt | Malden Center | malden center - adjust stop

## Sheet2
Weird Areas
Route_Name | Issue | Matches another Route? | Fix? | Loc Name
101-F-2 | Should use 20174, 25580, 25581, 25582 | 101-R-1 | Add points to shapes.txt
104-F-1 | Should use 97098, 102252, 51857 | 105-F-1, 109-F-1, 109-F-2 | Add points to shapes.txt | Sullivan Sq
104-R-1 | Should use 50780, 33019, 33024, 50788, 102827, 129369, 33020, 95912, 50787, 50788 | 105-R-1, 109-R-1 | Add points to shapes.txt | Sullivan Sq
105-F-1 | Should use 11113 |  | Fix DIR
106-F-2 | Should use Santilli Circle (10132, 10134, 10133, 10130) | 106-F2, 99-F-1, 110-F-1, 110-F-2, 112-R-1 | Fix DIR or add points to shapes.txt | Santilli Circle
106-R-1 | Missing stop 5859 |  | Unsure if we care - but it’s not a start or end stop.
106-R-2 | Should not be using (10132, 10134, 10133, 10130, 45358, 97039, 17319, 17321, 17320) |  | Absolutely no idea - add points to shapes.txt? This is odd behavior
11-R-1 | Should use (97364, 97363, 75113, 32751, 75112, 86649, 32750, 74989, 75116, 75115) | 47-F-1, 47-R-1, 9-R-1 | DIR issues?
112-F-1 | This route is bananas in the middle |  | add points to shapes.txt
112-R-1 | This route is bananas in the middle | 114-R-1 | Add points to shapes.txt
132-F-1 | doubles back at start/end of route |  | move last stop closer to available link
136-R-1 | doubles back incorrectly, may not care | 137-R-1 | move stop point (6771/6670)
16-R-3 | route end should take longer path | 16-R-4 | Add points to shapes.txt
170-F-1 | MassPike splits off incorrectly | 505-F-1 | Add points to shapes.txt
170-R-1 | MassPike splits off incorrectly, but dif direction so dif | 505-R-1 | Add points to shapes.txt
171-F-1 | Logan Airport is a mess | 741-F-1 | Add points to shapes.txt
195-R-1 | Should go between Public Gardens and Boston Common | 43-R-1, 55-R-2 | add points to shapes.txt
211-F-1 | wrong links at the end | 211-R-1, 217-F-1, 245-F-1, 245-R-1, 214-F-2, 214-F-3, 212-R-1, 214216-F-1, 215-R-1, 216-F-1, 220-F-1, 220-F-2, 221-F-1, 222-F-1, 222-F-2, 222-F-3, 225-F-1, 225-F-2, 225-F-3, 225-F-4, 225-F-5, 230-F-1, 236-F-1, 238-F-1, 238-F-2 | move stop point | Quincy Center | x
217-R-1 | end missing |  | investigate further | Quincy Center |  | SO MUCH BETTER - just quincy center issue
225-R-3 | end missing |  | investigate further | Quincy Center |  | SO MUCH BETTER - just quincy center issue
236-F-1 | weird loop back at end |  | investigate further | Quincy Center |  | SO MUCH BETTER - just quincy center issue
325-F-1 | broken connections on imported, so missing stops on conflated |  | investigate further |  |  | done
326-F-1 | missing a bunch of stops by taking a wrong turn | 326-R-1, 95-F-2, 95-R-1 | investigate further |  |  | done
34E-F-1 | odd middle bit | 34E-F-3, 34E-R-1, 34E-R-3, 35-F-2, 35-R-1, 52-F-1, 52-F-2, 52-R-1, 52-R-2 | update shapes.txt
350-F-1 | missing end of route? 350-F-2 has it though? |  | investigate further |  |  | done
354-F-1 | on the wrong link for a while in middle | 354-R-1 | update shapes.txt
36-R-1 | beginning of route missing |  | investigate further |  |  | done - deal with far stop from route
4-F-2 | should use 52751 and not go other direction |  | edit shapes.txt
4-R-1 | route begins on the wrong link/direction
40-F-1 | missing some links for stops at end of route
426-R-1 | takes wrong links in middle, unsure if worth fixing | 428-R-1 | edit shapes.txt
429-R-1 | odd interchange issues | 429-F-2, 429-F-3, 429-R-2 | edit shapes.txt
436-R-1 | shouldn't go through the interchange | 436-R-2, 436-F-2, 436-F-1, | move stops & edit shapes.txt
448-F-1 | stop on wrong side of link so makes odd choices (midpoint stop) & airport issues | 449-F-1 |  | * 449-R and 448-R have airport issues too
465-R-1 | odd route making odd choices |  | investigate further |  |  | not fixed at all
558-F-1 | missing big chunks of this route |  | investigate further |  |  | done
64-F-1 | missing end of the route |  | investigate further |  |  | done
67-R-1 | takes wrong link (33644) for short period | 62-R-1, 76-R-1, 84-R-1 | move stop
70-R-1 | missing last 3 stops |  | investigate further |  |  | done
708-R-1 | missing most of the route |  | investigate further |  |  | much better - cosmetic?
70A-F-1 | doesn't follow stops for last quarter of route |  | investigate further |  |  | done
71-F-1 | takes wrong link | 96-R-2, 72-R-1, 74-R-1, 75-R-1, 73-F-1, 71-R-1, 86-F-1, 78-R-1, 77-R-1, 73-R-1, 73-F-1, 746-F-1, 746-R-1, 75-F-1 | adjust shapes.txt to match R
716-F-1 | should not go on hwy | 716-R-1 | extend link to prevent going on hwy (or move stops to not go beyond link)
743-F-1 | really messed up route except for tunnel | 742-F-1, 741-F-1 | adjust shapes.txt
743-R-1 | beginning messed up but rest great | 742-R-1, 741-R-1 | adjust shapes.txt
747-R-1 | shortcuts |  | probably not big enough to require updates to shapes.txt
751-F-1 | South Station start/end |  | needs shapes.txt adjustment | South Station
76-R-1 | missing end/beginning of route |  | investigate further |  |  | much better - cosmetic
8-F-1/2 | weird middle and end |  | - adjust shapes.txt
8-R-1/2 | weird middle and end |  | - adjust shapes.txt
84-F-1 | route beginning oddly | 351-F-1, 62-F-1, 62-F-2, 67-F-1, 76-F-1 | adjust shapes.txt
86-F-1 | 2 loopy things missing - hwy? |  | adjust shapes.txt
88-R-1 | smaller loop at one end | 94-R-1, 96-R-1, 89-F-1 | adjust shapes.txt
99-F-1 | misses odd loop, hwy? | 132-R-1 | not a big deal - adjust shapes.txt